## Wotton
Deanery Strategic Pathway : Wotton | [7 empty] | Measuring progress throughout 26/27
Deanery Priority | Activities 26 | Granular Detail | Years 2 - 3 | Link to LIFE / Trellice | Metrics/KPIs | Deanery owner | Dependencies | Quarterly Commentary | Rag rating Q1 | Rag rating Q2 | Rag rating Q3 | Rag rating Q4
BUILDINGS | Develop a forum for a deanery-wide team of experts, suppliers and trades in order to service and maintain our buildings. | Deanery would like ability to submit work onto a portal so the suppliers can be added to a central database with reviews - CC to take this suggestion to the meeting on 29/04/26 |  | Building Trellis |  |  |  | Project turnkey - Meeting at diocese on 29/04/26 with Archdeacons, Buildings, SMT and Operations. Follow up meeting with buildings team - try to invite Mike B, Mike Hardwicke and Bob Copeland. - Ongoing discussions. | ▲
| Make the best use of what we have: Survey and review current church-building assets to see what patterns and potential arise for their best use, both as a resource and income stream. |  |  | Buildings Trellis |  |  |  | Review taking place by DOL on parish visits/inconjunction with clergy. Sharesey information provided. Buildings manual template - circulate with church wardens - mike to send Claire link. | ▲
| Eco church mapping and networking | [6 empty] | Complete - on mission and ministry document
FINANCIAL | Income Review and Development: Develop a programme to assist benefices and or parishes in reviewing their income streams, both current and potential. | Some excellent engagement around fundraising and x 1 benefice (badminton) has asked for help with creating fundrating strategy including for major donors. CC discussed with LK and LK will kindly support this, with a aim of LK/CC creating something scaleable/helpful to other benefices in the process. Tyndale Trail developement is on track, meeting set with graphic designer for mock up work, route planned, meeting to take to clergy/interested parties resheduled. Questionairre RE facilities in churches sent out. |  |  | Tyndale Trail launch September 2026 Develop x1 parish fundraising strategy by end of June aiming to create resources to disseminate more widely in the process. |  |  | Lisa Jane doing a deanery surgery in May - ongoing discussions at PCC meetings (stewardship and giving) Tyndale trail progress trackable via Monday, aiming for September launch in time for ride and stride. LK/CC to provide fundraising strategy support to Badminton, awaiting financials from Badminton to have pre meet. Add to agenda for next meeting regarding deanery finance governance. | ▲
Simplification and Reducing Costs: Work with benefices and parishes to review and develop schemes where it would be more beneficial to collaborate with each other.
| Help parishes to increasing their return on investment for fundraising activities | Some parishes frustrated by low attendance for community/fundraising events, however the events arent always advertised online. To help with FB event advertising as a test of change to assertain if a wider SM education campaign would be useful. |  |  | Measure attendance at events before and after increasing advertising. Hoping to achieve a minimum of 20% increase in attendance. |  |  | CC reached out to communications team to ask for deanery drop in sessions on SM for parishes. Wotton deanery FB page created to assist parishes with listing events on FB in the meantime. | ●
GOVERNANCE AND ADMINISTRATION | Deanery wide communications strategy | Logo created, colour scheme/identity chosen. Branding pack to be created for deanery to use if needed. Communications strategy needs to be developed including policies. |  | LIFE vision colours chosen, and branding selected to mirror Diocese and create unity. | Branding pack for the deanery by end of June. Page on the Diocese website through Sam by end of June. DSP to be published publically by end of June. | CC | Sam - website | Logo created and approved by DSPG 31/03/26. Agreement on branding approach (LIFE) and scale of branding pack to be developed for deanery use. Sam approached in March for a deanery page on diocesan website - agreement from DSPG this is sensible rather than pursing a website, hope for DSP to be on this webpage to allow those with google only software easy visability of DSP. Policies sent by Bob from his parish, CC to review deanery policies with aim of creating central resources. Full communications strategy to be developed including social media, (See fundraising tab).. - on track - Sam has date he advises website will be complete by. | ●
| Parish Reviews: Work with parishes and benefices to ensure they get the most out of the by working DSP on their own action plans to implement identified DSP priorities. |  |  |  | A complete DSP plan by end of June taking into account the parish information. From this, an easy to understand guide about the DSP to disseminate to parishes. Feedback to be sought on DSP guide in next quarter from parishes |  | Access needed across the deanery - some resistance encountered in x 1 benefice. | 01/04/26 - Currently on track. Missing interactions in a few parishes and x 1 benefice due to access issues. Now invited to remaining parishes/benefice with previous lack of engagement - hope to complete visits by end of quarter. 12/05/26- Chapter May 20th to discuss deanery roadmap - Aim to create this by end of June - need to colaborate with wider deanery to document 2-3 year goals. Aim for a deanery meeting september/october 26 to discuss longer term goals. - Collect data on building manual template. | ●
| Review vacancy and appointment process | Agreeement at deanery and DOL level this is a priority. Agreement amongst DOL to join forces for a joint meeting to look at this - time/date TBC. | [5 empty] | Vacancy process being mapped by CC for Carole/Claire to look at. Plan to take thoughts to meeting with other DOL/deanery representation. - on hold - now a diocese project - to continue to feedback. Discussion on current vacancies at next meeting. Diocese project to look at retirements for next 7 years to map vacancies considering pension changes.
| Explore ways of helping and supporting post holders in their roles | Post holder support already created by Carole/Joy - feedback across deanery positive regarding this. |  |  | Continued positive feedback from post holders that current system is providing support. |  |  | Started by Carole and Joy. Good feedback on post holder forums and group email support particularly from treasurers. Administrator meeting TBC - Carole/Joy arranging. When date agreed aim to do treasurers or churchwardens meeting same day. PSO meeting to be held within the deanery for the diocese September 14th 2026. | ●
| Survey and review benefice and parish administrators to get a complete sense of the task with a view to identifying areas of potential support, training, networking and sharing of administration. | [6 empty] | Administration reviews have been taking place as part of parish reviews. Need for support in areas where there is no administrator is clear. X1 benefice has no administrator and high burden of life events. Have been working with clergy to identify new systems of work. Signed up for a CMS system and date in diary by end of May to trial this and create database of previous life events connections to continue to support and connect with this community. Side benefit of online system being in use as we consider sucession planning. | ●
MISSION AND MINISTRY | Enable a proactive a mix of ordained, licensed and lay people working across benefice boundaries for the benefit of local expressions of mission and ministry. | Current courses not widely advertised across deanery/benefice boundaries. |  | Lay Leadership/Youth Connection |  |  |  | CC to ask M and M if any resources avaliable on creating team ministry. | ▲
| Use existing forums to share and celebrate good news to encourage, inspire and imitate. | Agreement to add this to synod at next synod. Consider additional channels? Feedback currently from deanery that current meetings are too buisness focused and not enough on "good news" or mission and ministry. | [5 empty] | Agreement to add this to synod at next synod. Consider additional channels?Social media training by year end. "Free text good news" on website. | ●
| Develop a deanery-level road map showing how to establish local mission and ministry teams covering discernment and training, enabling the sharing of best practices and celebrating together what God is doing amongst us. | Complete list of team ministry - to be presented at the next DSPG meeting. Invite mission and ministry/David Treherne to attend the next DSPG meeting to discuss opportunities. |  | Lay Leadership/Youth Connection | Deanery level road map to be completed by end of June to take to Synod. |  |  | Discussion at DSPG - Lists of where team/joined up ministry is happening and can this be shared? (Asked 31/03/26). Aim to discuss deanery level road map at next chapter with exercises, with aim to take a 1st draft of this work to Synod in July. Approached Sandra Millar 01/04/26 regarding someone from M and M attending next DSPG to discuss avaliable courses and provide input. Have been advised M and M can no longer support. Clergy started mapping, good collaboration/participation from all. | ▲
Criteria for the status
[7 empty] | × | = Not on track to meet targets and/or milestones
[7 empty] | ▲ | = At risk of not meeting targets and/or milestones
[7 empty] | ● | = On track to meet targets and milestones
[7 empty] | ◉ | = Work is complete
[7 empty] | ≈ | = Project as planned, is not due to start yet, or its start date has been pushed back